## Master — All Phases
Phase | Also In Phase | Blocks Go-Live? | Priority | Section | Field / Data Request | Field Type | Can Use Dummy? | Default Value / Assumption | Likely Source | Pre-Deploy Note | Post-Deploy Note | Mohegan — Have Today? | Notes (Original) | Added By
◆ PHASE 1 — EARLY ONBOARDING ¦ Gate checks before deployment is confirmed
Early Onboarding |  | Yes | High | 0. Pre-flight checks | OEM APIs available for robot models in scope? | Y/N check | N |  | MBody Ops / Tim | Verify before any deployment date is committed. |  |  | New gate requirement identified by Chris. Not in John's original map. | Chris (New)
Early Onboarding |  | Yes | High | 0. Pre-flight checks | New client or existing client? | Choice (New / Existing) | N |  | MBody CS / Sales | Answer determines whether full onboarding flow runs or partial. |  |  | New gate question. Not currently tracked in John's map. | Chris (New)
Early Onboarding |  | Yes | High | 0. Pre-flight checks | New location or existing location? | Choice (New / Existing) | N |  | MBody CS | Ask per location, not just per client — a returning client may add a new site. |  |  | New gate question. Not currently tracked in John's map. | Chris (New)
◆ PHASE 2 — PRE-DEPLOY ¦ Data collection and configuration before go-live
Pre-Deploy |  | Yes | High | 1. ROI targets | Primary ROI objective | Long text | N |  | Sales (during deal phase) |  |  |  | Customer-specific - cannot dummy. Sales picks up during deal phase per prior session. | John
Pre-Deploy |  | Yes | High | 1. ROI targets | Baseline annual cost of manual operations replaced ($) | Currency | Y | $17/hr + 20% overhead | Customer (Finance/Ops) |  |  |  | Standing assumption: $17/hr + 20% overhead. Use as dummy if customer can't supply. | John
Pre-Deploy |  | Yes | High | 1. ROI targets | Target sq ft cleaned per robot per day | Number | Y | 8 hrs/day utilization x robot speed | MBody (standard) + Customer override |  |  |  | Standing assumption: 8 hrs/day utilization x robot speed. | John
Pre-Deploy |  | Yes | High | 1. ROI targets | Target utilization hours per robot per day | Number | Y | 8 hrs/day per prior session | MBody (standard) + Customer override |  |  |  | Default 8 hrs/day per prior session. | John
Pre-Deploy |  | Yes | Medium | 1. ROI targets | Target cost reduction (%) | Number | Y | 25-30% if customer doesn't specify | Customer + Sales |  |  |  | Default 25-30% if customer doesn't specify. | John
Pre-Deploy |  | Yes | Medium | 1. ROI targets | Target payback period | Text | Y | 18-24 months if not specified | Customer + Sales |  |  |  | Default 18-24 months if not specified. | John
Pre-Deploy |  | Yes | Medium | 1. ROI targets | Non-financial ROI goals | Long text | N |  | Customer (GM/Ops) |  |  |  | Customer-specific narrative. | John
Pre-Deploy |  | Yes | Medium | 1. ROI targets | How ROI will be measured & reported | Long text | Y | standard MBody methodology | Customer + MBody CS |  |  |  | Use standard MBody methodology as dummy. | John
Pre-Deploy |  | Yes | High | 10. Time zone & reporting schedule | Primary operating time zone | Choice | Y |  | Property address (auto) + Customer confirm |  |  |  | Auto-detect from property address as dummy. | John
Pre-Deploy |  | Yes | Medium | 10. Time zone & reporting schedule | Additional time zones (multi-region customers) | Choice | Y |  | Customer |  |  |  |  | John
Pre-Deploy |  | Yes | Medium | 10. Time zone & reporting schedule | Business hours definition (per site) | Text | Y | Mon-Fri 06:00-22:00 | Customer (Site Manager) |  |  |  | Default: Mon-Fri 06:00-22:00. | John
Pre-Deploy |  | Yes | Medium | 10. Time zone & reporting schedule | Default robot schedule (start / dock times) | Time + time | Y | 12:00am start / 12:00am dock per prior session | Customer (Ops) |  |  |  | Default 12:00am start / 12:00am dock per prior session. | John
Pre-Deploy |  | No | Low | 10. Time zone & reporting schedule | Daily report delivery time (default 07:00 local) | Time | Y | 07:00 local per prior session | Customer |  |  |  | Default 07:00 local per prior session. | John
Pre-Deploy |  | No | Low | 10. Time zone & reporting schedule | Weekly report day & time (default Mon 07:30) | Day + time | Y | Monday 07:30 | Customer |  |  |  | Default Monday 07:30. | John
Pre-Deploy |  | No | Low | 10. Time zone & reporting schedule | Monthly report date & time (default 1st of month 08:00) | Date + time | Y | 1st of month 08:00 | Customer |  |  |  | Default 1st of month 08:00. | John
Pre-Deploy |  | Yes | High | 11. Document requests | Facility map (with time-of-day restrictions by area and go / no-go zones) | File upload (CAD / PDF / image) | N |  | Customer (Facilities + GM + Compliance) |  |  |  | Cannot dummy. Day 1 mapping walkthrough builds on this. Overlaps with section 3 floor plan field but adds the time and access overlay. | John
Pre-Deploy |  | Yes | High | 11. Document requests | Org chart / reporting structure | File upload (PDF / image / org chart) | Partial |  | Customer (HR / Ops Director) |  |  |  | Can scaffold from contact list as dummy; real org chart preferred for clean access setup. | John
Pre-Deploy |  | Yes | High | 11. Document requests | Vendor W-9 / banking details | File upload (W-9 PDF + ACH form) | N |  | Customer (AP / Procurement) |  |  |  | Cannot dummy. Common deployment delay if not captured up front. | John
Pre-Deploy |  | Yes | High | 2. KPIs & performance metrics | KPI selection (which of the 10 standard KPIs to track) | Multi-select from 10 | Y | to all 10 standard KPIs as dummy until customer narrows | Sales proposes, Customer confirms |  |  |  | Default to all 10 standard KPIs as dummy until customer narrows. | John
Pre-Deploy |  | Yes | High | 2. KPIs & performance metrics | Top headline KPI | Text | Y | to Avg Coverage as dummy headline | Customer (with Sales coaching) |  |  |  | Default to Avg Coverage as dummy headline. | John
Pre-Deploy |  | Yes | Medium | 2. KPIs & performance metrics | KPI reporting frequency | Text | Y | cadence per prior session | Customer |  |  |  | Default cadence per prior session. | John
Pre-Deploy | Post-Deploy | Yes | Medium | 2. KPIs & performance metrics | KPI targets & thresholds (per KPI) | Per-KPI numeric | Y | industry benchmarks | Customer + MBody CS | Use industry benchmarks as dummy targets | Refine using 2 weeks of real operational data |  | Use industry benchmarks as dummy targets; refine post-deploy. | John
Pre-Deploy |  | Yes | High | 3. Validate fleet & locations | Confirm total robot count in Orchestrator | Number | N |  | Customer (asset team) |  |  |  | Real count required - cannot dummy. | John
Pre-Deploy |  | Yes | High | 3. Validate fleet & locations | Confirm robot models / types are correct | Text | N |  | Customer + MBody Ops |  |  |  |  | John
Pre-Deploy |  | Yes | High | 3. Validate fleet & locations | Confirm number of sites / locations | Number | N |  | Customer (Property GMs) |  |  |  |  | John
Pre-Deploy | Post-Deploy | Yes | High | 3. Validate fleet & locations | Confirm floors / zones mapped correctly per site | Long text | Partial |  | Customer (Site Manager) + on-site walkthrough | Initial map from floor plan (estimate OK) | Final confirmation after Day 1 on-site walkthrough |  | Initial map from floor plan pre-deploy; final on Day 1. | John
Pre-Deploy |  | Yes | High | 3. Validate fleet & locations | Location / sub-location groupings for reporting | Long text | N |  | Customer (Ops Director) |  |  |  | Customer-specific hierarchy. | John
Pre-Deploy |  | Yes | High | 3. Validate fleet & locations | Floor plans (CAD, image, or written description) | File upload | N |  | Customer (Facilities) |  |  |  | Cannot dummy a floor plan. | John
Pre-Deploy |  | Yes | High | 3. Validate fleet & locations | Areas with names + size + floor type + cleaning hours | Per-area table | Partial |  | Customer (Facilities + Ops) |  |  |  | Estimate from floor plan as dummy; refine on Day 1. | John
Pre-Deploy |  | Yes | High | 3. Validate fleet & locations | Restricted zones (gaming floor, VIP suites, maintenance areas) | Long text | N |  | Customer (GM + Compliance) |  |  |  | Cannot dummy - regulator and customer-specific. | John
Pre-Deploy |  | Yes | Medium | 3. Validate fleet & locations | Amendments or corrections required | Long text | N |  | Customer |  |  |  | Empty by default; populated as issues found. | John
Pre-Deploy |  | Yes | High | 4. Contacts by location & role | Executive sponsor / owner (fleet-wide) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | High | 4. Contacts by location & role | Operations director (fleet-wide) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | High | 4. Contacts by location & role | Robot programme manager (fleet-wide) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | High | 4. Contacts by location & role | IT / network contact (fleet-wide) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | High | 4. Contacts by location & role | Site manager (per location) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | High | 4. Contacts by location & role | Cleaning / ops supervisor (per site) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | High | 4. Contacts by location & role | First responder - robot incidents (per site, 24/7) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | High | 4. Contacts by location & role | MBody AI technical account manager (MBody) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | High | 4. Contacts by location & role | Client PO approver - chargeable Break/Fix work (fleet-wide) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | High | 4. Contacts by location & role | GDPR / data sharing consent | Y/N | N |  | Customer (Legal/Privacy) |  |  |  | Cannot dummy - legal requirement. | John
Pre-Deploy |  | Yes | Medium | 4. Contacts by location & role | Finance & reporting contact (fleet-wide) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | Medium | 4. Contacts by location & role | Health & safety officer (per site) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | Medium | 4. Contacts by location & role | Billing / AR contact (fleet-wide) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | Medium | 4. Contacts by location & role | Defective parts collection contact (per site) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | Medium | 4. Contacts by location & role | Shift availability (hours/days) for each contact | Per-contact text | Partial | 24/7 as dummy until customer confirms | Customer |  |  |  | Default 24/7 as dummy until customer confirms. | John
Pre-Deploy |  | Yes | Medium | 4. Contacts by location & role | Organisational structure (zone leads, shift leads) | Long text | Y | flat structure as dummy | Customer (Ops Director) |  |  |  | Default flat structure as dummy. | John
Pre-Deploy |  | No | Low | 4. Contacts by location & role | Client feedback / CSAT contact (per site) - name, title, email, mobile | Contact card | N |  | Customer (HR/Ops) |  |  |  | Cannot dummy a real contact. Capture shift availability + alert tier (P1/P2/P3) for alert recipients. | John
Pre-Deploy |  | Yes | High | 5. Reporting roles & access | Fleet-wide report recipients | Long text | N |  | Customer (Ops Director) |  |  |  |  | John
Pre-Deploy |  | Yes | High | 5. Reporting roles & access | Site-specific report recipients | Long text | N |  | Customer (Ops Director) |  |  |  |  | John
Pre-Deploy |  | Yes | High | 5. Reporting roles & access | Who can amend robot schedules / settings? | Long text | N |  | Customer (Ops Director) |  |  |  |  | John
Pre-Deploy |  | Yes | High | 5. Reporting roles & access | Reporting access scope (all robots / by zone / by team) | Choice | N |  | Customer (Ops Director) |  |  |  | Customer-specific decision per prior session. | John
Pre-Deploy |  | Yes | High | 6. Alert configuration & routing | Out-of-hours critical alert contacts (with mobiles) | Contact list | N |  | Customer (Ops Director) |  |  |  | Cannot dummy - real numbers needed. | John
Pre-Deploy |  | Yes | High | 6. Alert configuration & routing | Break/Fix customer approval alert recipient | Contact | N |  | Customer (PO Approver) |  |  |  |  | John
Pre-Deploy |  | Yes | High | 6. Alert configuration & routing | Escalation chain by severity (who escalates to whom) | Per-priority chain | N |  | Customer (Ops Director) |  |  |  | Cannot dummy - real chain needed for Critical. | John
Pre-Deploy |  | Yes | Medium | 6. Alert configuration & routing | Alert delivery method per priority | Multi-choice | Y | email all priorities, SMS for Critical only | Customer (Ops + IT) |  |  |  | Default: email all priorities, SMS for Critical only. | John
Pre-Deploy |  | No | Low | 7a. Integrations - SSO / Identity | Integration required? (Required / In scope / Not required) | Choice | Y | Not required Q1; revisit Q2 | Customer (IT) |  |  |  | Default Not required Q1; revisit Q2. | John
Pre-Deploy |  | No | Low | 7b. Integrations - Task management / CMMS | Integration required? (Required / In scope / Not required) | Choice | Y |  | Customer (IT/Ops) |  |  |  |  | John
Pre-Deploy |  | Yes | High | 7c. Integrations - Facilities (Elevators, Access) | Integration required? (Required / In scope / Not required) | Choice | N |  | Customer (Facilities) + Tim |  |  |  | Tim owns elevator integration scoping per prior session. | John
Pre-Deploy |  | Yes | Medium | 7d. Integrations - Other (BI, BMS, Comms) | Additional platforms requested? (BI, BMS, Teams, Slack) | Long text | Y |  | Customer (BI/IT) |  |  |  | Per prior session: ask Q1, execute Q2. | John
Pre-Deploy |  | Yes | Medium | 7d. Integrations - Other (BI, BMS, Comms) | Integration purpose (what data flows where, why) | Long text | Y |  | Customer |  |  |  |  | John
Pre-Deploy |  | Yes | Medium | 7d. Integrations - Other (BI, BMS, Comms) | Technical contact per system | Contact | N |  | Customer (IT) |  |  |  |  | John
Pre-Deploy |  | Yes | High | 8. Field Service Mgmt & Work Orders | Client SLA tier (P1/P2/P3 response & resolution) | Choice | N |  | Contract / MBody Sales |  |  |  | Already in contract - confirm in Q1. | John
Pre-Deploy |  | Yes | High | 8. Field Service Mgmt & Work Orders | SLA service credit rate ($70/hr/robot or negotiated) | Currency | Y | $70/hr/robot | Contract / MBody Sales |  |  |  | Default $70/hr/robot. | John
Pre-Deploy |  | Yes | High | 8. Field Service Mgmt & Work Orders | Break/Fix approval method (email / portal / signature / verbal+email) | Choice | Y | email sign-off | Customer (PO Approver) |  |  |  | Default: email sign-off. | John
Pre-Deploy |  | Yes | High | 8. Field Service Mgmt & Work Orders | Break/Fix approval contact + turnaround expectation | Contact + duration | N |  | Customer (PO Approver) |  |  |  |  | John
Pre-Deploy |  | Yes | High | 8. Field Service Mgmt & Work Orders | WO service report delivery (recipients on WO close) | Long text | N |  | Customer (Ops) |  |  |  |  | John
Pre-Deploy |  | Yes | High | 8. Field Service Mgmt & Work Orders | PM schedule recurrence (default 14 days) | Number | Y | 14 days per prior session | MBody (default) + Customer override |  |  |  | Default 14 days per prior session. | John
Pre-Deploy |  | Yes | High | 8. Field Service Mgmt & Work Orders | PM completion report recipient | Contact | N |  | Customer (Ops) |  |  |  |  | John
Pre-Deploy |  | Yes | Medium | 8. Field Service Mgmt & Work Orders | Client portal access for live WO visibility? | Y/N | Y | no portal | Customer (Ops) |  |  |  | Default: no portal. | John
Pre-Deploy |  | Yes | Medium | 8. Field Service Mgmt & Work Orders | Client feedback / CSAT opt-in | Y/N | Y | opt-in | Customer (Ops) |  |  |  | Default: opt-in. | John
Pre-Deploy |  | Yes | Medium | 8. Field Service Mgmt & Work Orders | Damage classification process (who verifies damage type) | Long text | Y |  | Customer (Site Manager) |  |  |  | Standard process explanation as dummy. | John
Pre-Deploy |  | Yes | Medium | 8. Field Service Mgmt & Work Orders | Defective parts handover process + contact | Contact + process | Partial |  | Customer (Site) |  |  |  | Standard process as dummy; real contact required. | John
Pre-Deploy |  | Yes | Medium | 8. Field Service Mgmt & Work Orders | New robot commissioning contact (per site) | Contact | N |  | Customer (Site Manager) |  |  |  |  | John
Pre-Deploy |  | Yes | High | 9. Location insight reports | Report components selected (10 standard available) | Multi-select | Y |  | Sales proposes, Customer confirms |  |  |  | Standard 10 components - this IS the dummy report per prior session. | John
Pre-Deploy |  | Yes | High | 9. Location insight reports | KPI selection per insight report | Multi-select | Y | standard set | Sales + Customer |  |  |  | Use standard set as dummy. | John
Pre-Deploy |  | Yes | High | 9. Location insight reports | Report recipients at site level | Long text | N |  | Customer (Site Manager) |  |  |  |  | John
Pre-Deploy |  | Yes | High | 9. Location insight reports | Dummy report walkthrough completed? | Y/N | N |  | Sales + Customer |  |  |  | This IS the dummy step per prior session. | John
Pre-Deploy |  | Yes | Medium | 9. Location insight reports | Insight report frequency per site | Text | Y | daily email + weekly PDF + monthly deep-dive | Customer |  |  |  | Default: daily email + weekly PDF + monthly deep-dive. | John
Pre-Deploy |  | Yes | Medium | 9. Location insight reports | Preferred report format (email / dashboard / PDF / BI feed) | Choice | Y | email digest + dashboard | Customer |  |  |  | Default: email digest + dashboard. | John
Pre-Deploy | Post-Deploy | No | Low | 9. Location insight reports | Client BI / reporting tool integration (Power BI, Tableau) | Text | Y |  | Customer (BI/IT) | Identify tool and confirm requirement with customer | Execute the integration build |  | Ask Q1, execute Q2. | John
Pre-Deploy |  | No | Low | 9. Location insight reports | Benchmarking preference (vs other sites / industry / prior period) | Choice | Y | vs prior period | Customer |  |  |  | Default: vs prior period. | John
◆ PHASE 3 — DEPLOY ¦ Operational tasks at go-live (system setup, training, validation)
Deploy |  | Yes | High | 3. Validate fleet & locations | Robot register validation (per robot: ID, correct Y/N, amendment) | Per-robot table | N |  | Customer + MBody Ops | Reframed by Chris as Deploy operational task — not a pre-deploy data collection item |  |  |  | John
Deploy |  | Yes | High | Operational Deploy Tasks | Ingest robots; define robot alias, location and sub-location maps | Operational task | N |  | MBody Ops |  |  |  | Operational task — not a data collection item. Added by Chris. | Chris (New)
Deploy |  | Yes | High | Operational Deploy Tasks | Set report cadence in Orchestrator (daily / weekly / monthly delivery times) | Operational task | N | Daily 07:00 / Weekly Mon 07:30 / Monthly 1st 08:00 | MBody CS |  |  |  | Consolidates Sections 9 + 10 timing. Deploy configuration task. Added by Chris. | Chris (New)
Deploy |  | Yes | High | Operational Deploy Tasks | Validate access controls — each role logs in and confirms correct data scope | Operational task | N |  | MBody CS + Customer |  |  |  | New deploy verification step. Not currently tracked. | Chris (New)
Deploy |  | Yes | High | Operational Deploy Tasks | Orchestrator training for all customer user roles | Operational task | N |  | MBody CS |  |  |  | New deploy step. Not currently tracked. | Chris (New)
◆ PHASE 4 — POST-DEPLOY ¦ Confirmation, tuning and follow-on work (+2 weeks)
Post-Deploy |  | No | Medium | 12. Post-Deploy Review | Additional users, roles, reporting or training needed? (+2 week review) | Long text | N |  | MBody CS + Customer |  | Review at scheduled +2 week call. |  | New post-deploy review item identified by Chris. | Chris (New)
Post-Deploy |  | No | Low | 2. KPIs & performance metrics | Custom KPI or formula required? | Long text | Y | none | Customer + MBody CS |  |  |  | Park to Q2 unless customer raises it. Default: none. | John
Post-Deploy |  | No | Medium | 5. Reporting roles & access | Login method (SSO vs individual) | Text | Y | to individual email login Q1; revisit Q2 if customer raises SSO | Customer (IT) |  |  |  | Default to individual email login Q1; revisit Q2 if customer raises SSO. | John
Post-Deploy |  | No | Low | 6. Alert configuration & routing | Alert suppression / quiet hours | Text | Y | 22:00-06:00 quiet hours as dummy | Customer |  |  |  | Default 22:00-06:00 quiet hours as dummy. | John
Post-Deploy |  | No | Low | 6. Alert configuration & routing | Site-specific alert overrides | Long text | Y | no overrides | Customer (Site Managers) |  |  |  | Default: no overrides. | John
Post-Deploy |  | No | Low | 6. Alert configuration & routing | Priority threshold tuning (P1/P2/P3 triggers) | Per-priority config | Y |  | MBody (default) + Customer (refine) |  |  |  | Use defaults Q1, tune Q2. | John
Post-Deploy |  | No | Low | 7a. Integrations - SSO / Identity | Identity provider (Azure AD, Okta, Google, ADFS) | Text | Y |  | Customer (IT) |  |  |  |  | John
Post-Deploy |  | No | Low | 7a. Integrations - SSO / Identity | SSO protocol (SAML 2.0, OIDC, OAuth 2.0) | Choice | Y |  | Customer (IT) |  |  |  |  | John
Post-Deploy |  | No | Low | 7a. Integrations - SSO / Identity | Tenant ID / domain | Text | Y |  | Customer (IT) |  |  |  |  | John
Post-Deploy |  | No | Low | 7a. Integrations - SSO / Identity | User provisioning method (manual / SCIM / JIT) | Choice | Y |  | Customer (IT) |  |  |  |  | John
Post-Deploy |  | No | Low | 7a. Integrations - SSO / Identity | Group / role mapping | Long text | Y |  | Customer (IT) |  |  |  |  | John
Post-Deploy |  | No | Low | 7a. Integrations - SSO / Identity | IT contact for SSO setup | Contact | N |  | Customer (IT) |  |  |  |  | John
Post-Deploy |  | No | Low | 7b. Integrations - Task management / CMMS | Task / CAFM / CMMS platform | Text | Y |  | Customer (IT/Facilities) |  |  |  |  | John
Post-Deploy |  | No | Low | 7b. Integrations - Task management / CMMS | Integration method (API / webhook / email / CSV) | Choice | Y |  | Customer (IT) |  |  |  |  | John
Post-Deploy |  | No | Low | 7b. Integrations - Task management / CMMS | API endpoint / base URL | Text | N |  | Customer (IT) |  |  |  |  | John
Post-Deploy |  | No | Low | 7b. Integrations - Task management / CMMS | Authentication method | Text | N |  | Customer (IT) |  |  |  |  | John
Post-Deploy |  | No | Low | 7b. Integrations - Task management / CMMS | Which robot events create tasks? | Long text | Y |  | Customer (Ops + MBody CS) |  |  |  |  | John
Post-Deploy |  | No | Low | 7b. Integrations - Task management / CMMS | Task priority mapping (Orchestrator severity to CMMS priority) | Long text | Y |  | Customer + MBody CS |  |  |  |  | John
Post-Deploy |  | No | Low | 7b. Integrations - Task management / CMMS | Task assignee / queue routing | Long text | Y |  | Customer (Ops) |  |  |  |  | John
Post-Deploy |  | No | Low | 7b. Integrations - Task management / CMMS | Completion status sync back to Orchestrator? | Y/N | Y |  | Customer + MBody CS |  |  |  |  | John
Post-Deploy |  | No | Medium | 7c. Integrations - Facilities (Elevators, Access) | Elevator system / vendor (KONE, Otis, Schindler) | Text | Y |  | Customer (Facilities) |  |  |  |  | John
Post-Deploy |  | No | Medium | 7c. Integrations - Facilities (Elevators, Access) | Access control / door system (Genetec, Lenel, HID, Brivo) | Text | Y |  | Customer (Facilities + Security) |  |  |  |  | John
Post-Deploy |  | No | Medium | 7c. Integrations - Facilities (Elevators, Access) | Floors / zones requiring elevator access | Long text | Partial |  | Customer (Facilities) |  |  |  | Estimate from floor plan. | John
Post-Deploy |  | No | Medium | 7c. Integrations - Facilities (Elevators, Access) | Doors / restricted areas requiring access | Long text | Partial |  | Customer (Facilities + Security) |  |  |  |  | John
Post-Deploy |  | No | Medium | 7c. Integrations - Facilities (Elevators, Access) | Facilities / building services contact | Contact | N |  | Customer (Facilities) |  |  |  |  | John
Post-Deploy |  | No | Low | 7c. Integrations - Facilities (Elevators, Access) | Integration method (API / BACnet / SDK / webhook) | Choice | Y |  | Customer (IT/Facilities) |  |  |  |  | John
Post-Deploy |  | No | Low | 7c. Integrations - Facilities (Elevators, Access) | Authentication method | Text | N |  | Customer (IT) |  |  |  |  | John
Post-Deploy |  | No | Low | 7c. Integrations - Facilities (Elevators, Access) | Failover behaviour (what robot does if integration fails) | Text | Y |  | MBody (default) |  |  |  | Use MBody default. | John
Post-Deploy |  | No | Low | 7d. Integrations - Other (BI, BMS, Comms) | Integration method (API / webhook / embedded dashboard / data feed) | Choice | Y |  | Customer (IT) |  |  |  |  | John
Post-Deploy |  | No | Medium | 9. Location insight reports | +2 week post-deploy validation: real data matches expectations? | Y/N | N |  | MBody CS |  |  |  | Post-deploy only. | John
Post-Deploy |  | No | Low | 9. Location insight reports | Insight report KPI targets need adjustment? (post-deploy) | Long text | N |  | Customer + MBody CS |  |  |  | Post-deploy only. | John

## Phase Summary
MBody Orchestrator — 4-Phase Onboarding Map ¦ Phase Summary
Source: John's Onboarding Data Map (v3, 28 Apr 26) reconciled with Chris's 4-Phase Must-Haves. Questions assigned to individual phase. "Partial" items appear in both Pre-Deploy and Post-Deploy.
Phase | Section | # Questions | High Priority | Blocks Go-Live? | Has New Items? | Key Note
PHASE 1 — EARLY ONBOARDING · 3 questions total · 3 block go-live
Early Onboarding | 0. Pre-flight checks | 3 | 3 | 3 | Yes | Gate questions — drive whether full onboarding runs or partial
PHASE 2 — PRE-DEPLOY · 82 questions total · 74 block go-live
Pre-Deploy | 1. ROI targets | 8 | 4 | 8 |  | All Pre-Deploy; ROI framing must be confirmed before go-live
Pre-Deploy | 10. Time zone & reporting schedule | 7 | 1 | 4 |  | All Pre-Deploy; cadence configuration is Deploy operational task
Pre-Deploy | 11. Document requests | 3 | 3 | 3 |  | All Pre-Deploy; facility map and W-9 are common blockers
Pre-Deploy | 2. KPIs & performance metrics | 4 | 2 | 4 |  | KPI thresholds span Pre-Deploy + Post-Deploy (refine with live data)
Pre-Deploy | 3. Validate fleet & locations | 9 | 8 | 9 |  | Robot register validation moved to Deploy phase by Chris
Pre-Deploy | 4. Contacts by location & role | 17 | 10 | 16 |  | Cannot use dummy data — real contacts required for all High items
Pre-Deploy | 5. Reporting roles & access | 4 | 4 | 4 |  | Login method (SSO) pushed to Post-Deploy; access scope is Pre-Deploy
Pre-Deploy | 6. Alert configuration & routing | 4 | 3 | 4 |  | Alert suppression + priority tuning parked to Post-Deploy
Pre-Deploy | 7a. Integrations - SSO / Identity | 1 | 0 | 0 |  | Gate Q is Pre-Deploy; all implementation details are Post-Deploy
Pre-Deploy | 7b. Integrations - Task management / CMMS | 1 | 0 | 0 |  | Gate Q is Pre-Deploy; all implementation details are Post-Deploy
Pre-Deploy | 7c. Integrations - Facilities (Elevators, Access) | 1 | 1 | 1 |  | Gate Q is Pre-Deploy; Tim owns elevator scoping
Pre-Deploy | 7d. Integrations - Other (BI, BMS, Comms) | 3 | 0 | 3 |  | Ask Q1; execute Q2 — BI integration spans both phases
Pre-Deploy | 8. Field Service Mgmt & Work Orders | 12 | 7 | 12 |  | All Pre-Deploy; SLA tier must match signed contract
Pre-Deploy | 9. Location insight reports | 8 | 4 | 6 |  | Most Pre-Deploy; +2wk validation and KPI tuning are Post-Deploy
PHASE 3 — DEPLOY · 5 questions total · 5 block go-live
Deploy | 3. Validate fleet & locations | 1 | 1 | 1 |  | Robot register validation moved to Deploy phase by Chris
Deploy | Operational Deploy Tasks | 4 | 4 | 4 | Yes | Operational system tasks — not data collection. All block go-live.
PHASE 4 — POST-DEPLOY · 31 questions total · 0 block go-live
Post-Deploy | 12. Post-Deploy Review | 1 | 0 | 0 | Yes | Review follow-on needs at +2 week call
Post-Deploy | 2. KPIs & performance metrics | 1 | 0 | 0 |  | KPI thresholds span Pre-Deploy + Post-Deploy (refine with live data)
Post-Deploy | 5. Reporting roles & access | 1 | 0 | 0 |  | Login method (SSO) pushed to Post-Deploy; access scope is Pre-Deploy
Post-Deploy | 6. Alert configuration & routing | 3 | 0 | 0 |  | Alert suppression + priority tuning parked to Post-Deploy
Post-Deploy | 7a. Integrations - SSO / Identity | 6 | 0 | 0 |  | Gate Q is Pre-Deploy; all implementation details are Post-Deploy
Post-Deploy | 7b. Integrations - Task management / CMMS | 8 | 0 | 0 |  | Gate Q is Pre-Deploy; all implementation details are Post-Deploy
Post-Deploy | 7c. Integrations - Facilities (Elevators, Access) | 8 | 0 | 0 |  | Gate Q is Pre-Deploy; Tim owns elevator scoping
Post-Deploy | 7d. Integrations - Other (BI, BMS, Comms) | 1 | 0 | 0 |  | Ask Q1; execute Q2 — BI integration spans both phases
Post-Deploy | 9. Location insight reports | 2 | 0 | 0 |  | Most Pre-Deploy; +2wk validation and KPI tuning are Post-Deploy
LEGEND
Early Onboarding — Gate questions before deployment is confirmed
Pre-Deploy — Data collected before go-live
Pre-Deploy + Post-Deploy — Collected as estimate pre-deploy; confirmed/refined post-deploy
Deploy — Operational system tasks at go-live (not data collection)
Post-Deploy — Confirmation, tuning and follow-on work at +2 weeks